SECTION 01320 - CONSTRUCTION PROGRESS DOCUMENTATION (Forthcoming Section 013200)

GENERAL

RELATED DOCUMENTS

Drawings and general provisions of the Contract, including General and Supplementary Conditions and Division 2 Specification Sections, apply to this Section.

SUMMARY

This Section includes administrative and procedural requirements for documenting the progress of construction during performance of the Work, including the following:

Contractor's Construction Schedule.

Submittals Schedule.

Daily construction reports.

Field condition reports.

Lowe's Development and Design Criteria Section 800 “Stormwater Pollution Prevention Plan” Ledger

See Division 00 for submitting Schedule of Values.

See Division 2 Section "Payment Procedures" for submitting the Schedule of Values.

See Division 2 Section "Photographic Documentation" for submitting construction photographs.

DEFINITIONS

Activity:  A discrete part of a project that can be identified for planning, scheduling, monitoring, and controlling the construction project.  Activities included in a construction schedule consume time and resources.

Critical activities are activities on the critical path.  They must start and finish on the planned early start and finish times.

Predecessor Activity:  An activity that precedes another activity in the network.

Successor Activity:  An activity that follows another activity in the network.

CPM:  Critical path method, which is a method of planning and scheduling a construction project where activities are arranged based on activity relationships.  Network calculations determine when activities can be performed and the critical path of Project.

Critical Path:  The longest connected chain of interdependent activities through the network schedule that establishes the minimum overall Project duration and contains no float.

Float:  The measure of leeway in starting and completing an activity.

Float time belongs to Owner

Fragnet:  A partial or fragmentary network that breaks down activities into smaller activities for greater detail.

Major Area:  A story of construction, a separate building, or a similar significant construction element.

SUBMITTALS

Submittals Schedule:  Submit four (4) copies of schedule.  Submit to Owner within 14 days following contract award. Arrange the following information in a tabular format:

Scheduled date for first submittal.

Specification Section number and title.

Submittal category (action or informational).

Name of subcontractor.

Description of the Work covered.

Scheduled date for Architect's final release or approval.

Contractor's Construction Schedule:  Submit three (3) printed opaque copies of initial schedule, large enough to show entire schedule for entire construction period.

The Contractor shall submit to the Owner within fourteen (14) days following the contract award both a graphic and an electronic copy of schedule, using software indicated, on CD-R, and labeled to comply with requirements for submittals.  The Construction Schedule Chart shall be as detailed as practical and shall show:

The project name

The Contractor’s name

The date of submittal

Each major term of work

The proposed start date, duration, and completion date of each item of work,

The actual start date, duration and completion date of each item of work.

CPM Reports:  Concurrent with CPM schedule, submit three copies of each of the following computer-generated reports.  Format for each activity in reports shall contain activity number, activity description, cost and resource loading, original duration, remaining duration, early start date, early finish date, late start date, late finish date, and total float in calendar days.

Daily Construction Reports:  Submit two copies at weekly intervals.

Field Condition Reports:  Submit two copies at time of discovery of differing conditions.

COORDINATION

Coordinate preparation and processing of schedules and reports with performance of construction activities and with scheduling and reporting of separate contractors.

Coordinate Contractor's Construction Schedule with the Schedule of Values, list of subcontracts, Submittals Schedule, progress reports, payment requests, and other required schedules and reports.

Secure time commitments for performing critical elements of the Work from parties involved.

Coordinate each construction activity in the network with other activities and schedule them in proper sequence.

PRODUCTS

SUBMITTALS SCHEDULE

Preparation:  Submit a schedule of submittals, arranged in chronological order by dates required by construction schedule.  Include time required for review, resubmittal, ordering, manufacturing, fabrication, and delivery when establishing dates.

Coordinate Submittals Schedule with list of subcontracts, the Schedule of Values, and Contractor's Construction Schedule.

Submit concurrently with the first complete submittal of Contractor's Construction Schedule.

CONTRACTOR'S CONSTRUCTION SCHEDULE, GENERAL

Time Frame:  Extend schedule from date established for commencement of the Work to date of Final Completion.

Contract completion date shall not be changed by submission of a schedule that shows an early completion date, unless specifically authorized by Change Order.

Milestones:  Include milestones indicated in the Contract Documents in schedule, including, but not limited to, the Notice to Proceed, Substantial Completion, and Final Completion

CONTRACTOR'S CONSTRUCTION SCHEDULE (CPM SCHEDULE)

General:  Prepare network diagrams using AON (activity-on-node) format.

Preliminary Network Diagram:  Submit diagram within 14 days of date established for the Notice of Award.  Outline significant construction activities for the duration of the Work.

CPM Schedule:  Prepare Contractor's Construction Schedule using a computerized time-scaled CPM network analysis diagram for the Work.

Develop network diagram in sufficient time to submit CPM schedule so it can be accepted for use no later than 30 days after date established for the Notice of Award.

Failure to include any work item required for performance of this Contract shall not excuse Contractor from completing all work within applicable completion dates, regardless of Architect's approval of the schedule.

Establish procedures for monitoring and updating CPM schedule and for reporting progress.  Coordinate procedures with progress meeting and payment request dates.

Use "one workday" as the unit of time.  Include list of nonworking days and holidays incorporated into the schedule.

CPM Schedule Preparation:  Prepare a list of all activities required to complete the Work.  Using the preliminary network diagram, prepare a skeleton network to identify probable critical paths.

Activities:  Indicate the estimated time duration, sequence requirements, and relationship of each activity in relation to other activities.  Include estimated time frames for all work.

Critical Path Activities:  Identify critical path activities, including those for interim completion dates.  Scheduled start and completion dates shall be consistent with Contract milestone dates.

Processing:  Process data to produce output data on a computer-drawn, time-scaled network.  Revise data, reorganize activity sequences, and reproduce as often as necessary to produce the CPM schedule within the limitations of the Contract Time.

Format:  Mark the critical path.  Locate the critical path near center of network; locate paths with most float near the edges.

Sub networks on separate sheets are permissible for activities clearly off the critical path.

Initial Issue of Schedule:  Prepare initial network diagram from a list of straight "early start-total float" sort.  Identify critical activities.  Prepare tabulated reports showing the following:

Contractor or subcontractor and the Work or activity.

Description of activity.

Principal events of activity.

Immediate preceding and succeeding activities.

Early and late start dates.

Early and late finish dates.

Activity duration in workdays.

Total float or slack time.

Average size of workforce.

Schedule Updating:  Concurrent with making revisions to schedule, prepare tabulated reports showing the following:

Identification of activities that have changed.

Changes in early and late start dates.

Changes in early and late finish dates.

Changes in activity durations in workdays.

Changes in the critical path.

Changes in total float or slack time.

Changes in the Contract Time.

REPORTS

Daily Construction Reports:  Prepare a daily construction report recording the following information concerning events at Project site:

Contractor’s name

Project Location

Work Progress for the Day

List of subcontractors at Project site.

Number of workmen by trade employed on the project for that day

Equipment at Project site.

Material deliveries.

High and low temperatures and general weather conditions.

Accidents.

Stoppages, delays, shortages, and losses.

Meter readings and similar recordings.

Orders and requests of authorities having jurisdiction.

Services connected and disconnected.

Equipment or system tests and startups.

Daily observation of level of sediment tracking at construction entrance/exit

Daily observation of proper use and disposal of chemicals and substances stored or used on site.

The Contractor shall submit to the Owner at the end of each week Daily Progress Reports for each day of work during the preceding week. A report shall be submitted for each day of the contract duration even if no work is performed. Copies of reports shall be maintained at the site by the Project Superintendent.

Field Condition Reports:  Immediately on discovery of a difference between field conditions and the Contract Documents, prepare and submit a detailed report.  Submit with a request for interpretation (RFI) to the Owner.  Include a detailed description of the differing conditions, together with recommendations for changing the Contract Documents.

LOWE’S STORM WATER POLLUTION PREVENTION PLAN (SWPPP) LEDGER

Required Record Keeping:  Prepare and maintain as required by the written SWPPP all inspection, maintenance and construction activity reports for the Project site. Required reports include, but are not limited to the following:

Contractor’s NPDES Operator Certification Signature Page (only where Contractor is also considered an “Operator” for the Project)

Form A-1 Signatory Authorization Designation Form (only where Contractor is also considered an “Operator” for the Project).

Form B-1 General Contractor’s Certification Form

Form B-2 Subcontractor’s Certification Form (for all subcontractors working on site)

Form C-1 Weekly (and Rain Event) Inspection Report for each required inspection.

Form C-2 Compliance Inspection Report (for Lowe’s Projece Manager and Third Party Inspector (when used)).

Form C-3 Corrective Action Log

Form D-1 Modification Report

Form E-1 Subcontractor Training Report Form

Form F-1 Final Inspection and Pre-Notice of Termination Report

Form G-1 Critical Incident and Reportable Quantity Form

Form G-2 SPCC Self-Certification Statement

Form G-3 SPCC Facility Description and Potential Tank Equipment and Operational Equipment Failure Resulting in Spills

Form H-1 Rainfall Log

Form I-1 Construction Site Notice

Form J-1 Pre-Construction Training Meeting Agenda

Site Map(s) (to record locations of materials management measures throughout construction and document Modificaitons to the plan)

Any additional Federal, State or Local Forms, Reports, or Certifications incorporated into the written SWPPP.

The Contractor shall submit to the Owner at the end of each month all Daily Progress Reports for each day of work during the preceding week. A report shall be submitted for each day of the contract duration even if no work is performed. Copies of reports shall be maintained at the site by the Project Superintendent.

Field Condition Reports:  Immediately on discovery of a difference between field conditions and the Contract Documents, prepare and submit a detailed report.  Submit with a request for interpretation (RFI) to the Owner.  Include a detailed description of the differing conditions, together with recommendations for changing the Contract Documents.

EXECUTION

CONTRACTOR'S CONSTRUCTION SCHEDULE

Contractor's Construction Schedule Updating:  At monthly intervals, update schedule to reflect actual construction progress and activities.  Issue schedule one week before each regularly scheduled progress meeting.

Revise schedule immediately after each meeting or other activity where revisions have been recognized or made.  Issue updated schedule concurrently with the report of each such meeting.

Include a report with updated schedule that indicates every change, including, but not limited to, changes in logic, durations, actual starts and finishes, and activity durations.

As the Work progresses, indicate Actual Completion percentage for each activity.

Distribution:  Distribute copies of approved schedule to Architect Owner, separate contractors, testing and inspecting agencies, and other parties identified by Contractor with a need-to-know schedule responsibility.

Post copies in Project meeting rooms and temporary field offices.

When revisions are made, distribute updated schedules to the same parties and post in the same locations.  Delete parties from distribution when they have completed their assigned portion of the Work and are no longer involved in performance of construction activities.

END OF SECTION 01320

- PROJECT LOWE’S OF ANYWHERE	CONTRACTOR LIGHTNING CONSTRUCTION	DATE OF REPORT _____________

- PROJECT ____________________	CONTRACTOR ___________________________		DATE OF REPORT _________________