## Sheet1
Lowe's Home Improvement |  |  |  | Project: | Lowe's - WESTLAKE, FL
Pre-Concrete Conference Agenda |  |  |  | Date:
Time:
Successful projects start with well planned concrete placements. Attention must be paid to all details, including proper concrete mixes, placement and finishing procedures, and curing. Special attention must be paid to column, wall and “core area” details. Ample working time and lighting must be available to ensure a successful placement.
1. Roll Call / Introduction of Attendees:
General Contractor | R/M Producer | Concrete Contractor | Testing Laboratory | Owner’s Representative | Densifier Applicator | Euclid Chemical
Euclid Chemical
Phil Brandt
1. Jobsite Orientation:
A. Interior Slab First: No walls or roof, slab unprotected and placed first
B. Interior Slab Last: Walls up/roof on, slab is protected and placed last
2. Concrete Placement Dates:
A. Planned Date of Interior Concrete Placement / Yardage: |  |  |  |  | Date | cyds.
B. Planned Date of Exterior Concrete Placement / yardage: |  |  |  |  | Date | cyds.
C. Plant Name
D. Plant to Jobsite Trip Time
E. Noise Issues?
F. Start Time
G. Trucks per Hour | [5 empty] | 80-100 cyds./hr.
H. Concrete Deposit Method: Truck / Buggy / Pump
I. Initial Load Testing: Slump and Air Test on First Load to Confirm Proper Mix
3. Subgrade / Vapor Retarder:
A. Subgrade / Base
B. Proof Rolling / Testing (Depressions deeper than ½" must be repaired)
C. Base Tolerances (+0" /-3/4" measured from bottom of slab elevation)
D. Vapor Retarder Type and Installation
E. Typical Sequence: Base / Vapor Retarder / Mesh / Concrete/Fiber
4. Interior Concrete Mix Review:
A. Interior Sales Floor Slab Concrete Mix Number:
B. Compressive | [5 empty] | 4000psi
C. Water/Cement Ratio (.53 max)
D. Slump | [5 empty] | 5.5"
E. Maximum Allowable Slump | [5 empty] | 6.5"
F. Air Content |  |  | Entrapped Air Only |  |  | 3.0% (max.)
G. Water |  |  | Normal / Hot / Chilled |  |  | GTC: Hot / Cold
H. Admixtures |  |  | Normal / Accelerator / Retarder |  |  | GTC: NCA / Ret
J. Prohibited: Fly Ash, Chloride or admixtures containing more than 0.05% chloride | [5 empty] | Check
K. Concrete Contractor Approval of Concrete Mix
5. Exterior Concrete Mix Review:
A. Exterior Slab Concrete Mix Number:
B. Compressive | [5 empty] | 4000psi
C. Water/Cement Ratio (.45 max)
D. Slump | [5 empty] | 5.5"
E. Maximum Allowable Slump | [5 empty] | 6.5"
F. Air Content |  |  | Air Entrained - 5% ± 1% |  |  | 4% - 6%
G. Water |  |  | Normal / Hot / Chilled |  |  | GTC: Hot / Cold
H. Admixtures |  |  | Normal / Accelerator / Retarder |  |  | GTC: NCA / Ret
I. Tuf-Strand SF Macro Fiber (lbs./cyd??)
J. Prohibited: Calcium Chloride or admixtures containing more than 0.05% chloride | [5 empty] | Check
K. Concrete Contractor Approval of Concrete Mix
6. Concrete Placing Plan:
A. Interior Sales Floor |  |  | Number of Placements / Finishes Required
B. Exterior Concrete |  |  | Finishes Required
C. Lighting Requirements |  |  | Ample lighting as necessary
D. Carbonation / Ventilation |  |  | Minimize exhaust gases during placement
E. Placement Plan |  |  | Left to right / back to front
F. Cold / Hot Weather Placing Plan |  |  | Normalize Set / Protection Plan
7. Interior Concrete Finishes Required:
A. Laser Screed |  |  |  | S-485 | S-940
B. Strike Off / Floating Consolidation |  |  | Pans / Combo’s
C. Re-straightening |  |  | Highway Straightedge
D. Troweling |  |  | Hard Steel Troweled Finish
E. Details: Columns, walls and “Core” area, including Bathroom and Managerial Areas
G. Interior Sales Floor Tolerance | [5 empty] | FF50/FL35
8. Additional Concrete Finishes Required:
A. Garden Center |  |  | Broom Finish / Sloped / No fibers showing |  |  | Yes
9. Curing and Protection:
A. Interior Sales Floor:
1. Product |  |  | Kurez DR VOX or Kurez DR 100
2. Application Rate |  |  | 400 sf / gallon
3. Sequencing of Cure / Measure / Cut |  |  |  | Cure / Measure / Cut
B. Exterior Concrete:
1. Product |  |  | Super Rez Seal or Super Diamond Clear VOX
2. Application Rate |  |  | 400 sf / gallon
3. Timing of Cure |  |  | Immediately following final broom
10. Construction and Contraction Joints:
A. Layout of Joints as per submitted and approved plan | [5 empty] | Per Plan
B. Saw to be Used
C. Condition of Soff-Cut Saw |  |  | New Blade and Plate (No Scratches!)
D. Depth of Cut |  |  | Interior (1/4d) | Tuf-Strand SF (1/3d)
E. Depth of Cut Verification by Testing Laboratory | [5 empty] | Yes
11. Interior Sales Joint Filling & Densifier Process:
A. Joint Filling
1. Building Condition |  |  | Building enclosed
2. Temperature / Climate Control |  |  | Thermastatically controlled?
3. Product |  |  | QWIKjoint UVR
B. Liquid Densifier / Sealer
1. Product |  |  | Euco Diamond Hard
2. Initial Application Rate |  |  | 225 sf / gallon
12. Interior Sales Floor Polishing Process:
A. Polishing Per Specification
B. Second Application of Liquid Densifier |  |  | 700 sf / gallon
C. Burnishing
D. Polishing Results |  |  | Gloss Factor of ≥35
E. Details at Walls and Fixtures |  |  | No White Residue/Clean within 3"
13. Testing Procedures:
A. Sub-grade Testing: |  |  | Procedures / Reports / Results
B. Concrete Testing:
1. Onsite Technician Certification
2. Storage / Protection |  |  | Thermastatically Controlled?
3. Cylinder Size | [5 empty] | 4"x 8"
4. Frequency |  |  | Every ?? Cyds |  |  | 50 cyds
5. Number of Cylinders |  |  |  |  | (0) 3 / (1) 7 / (3) 28 / (1) Hold
C. Air Content Control
1. Air meter type |  |  | ASTM C-231 or ASTM C-173 |  |  | ASTM C-231
2. How often required? |  |  | Sales Floor – Confirm no air-entrainment
D. Slump Control / Load Rejection |  |  |  | Lab to report / concrete contractor / general contractor
E. Floor profile test
1. Type instrument |  |  | Dipstick, F-Meter, D-Meter or Profileograph
2. Path of measuring lines |  |  | Type of Reading |  |  | Grid
3. Reporting time |  |  | Within 24 hours of slab placement |  |  | Yes
15. Parties receiving reports | [5 empty] | Attendees
Notes: